## Sheet1
To Do During Phase 1
Task | Python Status | Python Owner | PHP Status | PHP Owner
Figure out user roles (contact MLS admins or get list from API). Also add to config file - describe in design doc too | Done | Harold Hodgins | N/A | N/A
Figure out which grade items allow for grades > 100 | Done | Harold Hodgins | N/A | N/A
To Do Prior to Phase 3 | All of the answers to these tasks should be added to the Design doc
Task | Python Status | Python Owner | PHP Status | PHP Owner
Figure out how to handle concurrent users | In-Progress | Jacob Heard
Figure out logging | In-Progress | Harold Hodgins
Design JSON objects for communication between ezMarker front and back-end | Done | Troy Nechanicky | N/A | N/A
All phases should be completed in Python first, tested, then implmented in PHP, then tested in PHP
Phase 1: Wrapper API Functions File | Python Deadline: Nov. 4
Segment | Python Status | Python Owner | Testing Status | Testing Owner | PHP Status | PHP Owner | Testing Status | Testing Owner
update_route, get, put, check_request | Done | Luc Boulanger |  | Amardeep Sarang | In-Progress | Kosta Kalenteridis, SJ | Done | Shuaib Reeyaz
get_grade_items, put_grade_item, put_grade | Done | Jacob Heard |  | Mark Kokanovic | In-Progress | Kosta Kalenteridis, SJ | Done | Shuaib Reeyaz
get_user_enrollments, get_who_am_i | Done | Luc Boulanger | In-Progress | Deep Raithatha | In-Progress | Jaenuz Gorospe & Kosta Kalenteridis, SJ |  | Andrew Chua
get_course_enrollments, get_api_versions | Done | Chongju Mai | In-Progress | Kosta Kalenteridis | In-Progress | Jaenuz Gorospe, SJ | In-Progress | Simon Phothitay
Phase 2: Wrapper Classes | Python Deadline: Nov. 11
Segment | Python Status | Python Owner | Testing Status | Testing Owner | PHP Status | PHP Owner | Testing Status | Testing Owner
Host | Done | Luc Boulanger | In-Progress | Kosta Kalenteridis | In-Progress | Jaenuz Gorospe & Mohamed Al-Thibeh, SJ |  | Andrew Chua
OrgMember, User (One file) | Done | Jacob Heard | In-Progress | Andrew Chua | In-Progress | Andrew Chua, SJ | Done | Shuaib Reeyaz
Course | Done | Chongju Mai | In-Progress | Pirajeev Praba | In-Progress | Andrew Chua, SJ | In-Progress | Harjodh Singh
GradeItem, NumericGradeItem (One file) | Done | Luc Boulanger | In-Progress | Sumeet Jhand | In-Progress | Kosta Kalenteridis, SJ | Done | Shuaib Reeyaz
Grade, NumericGrade (One file) | Done | Xiang Ke | In-Progress | Simon Phothitay | In-Progress | Simranjit Dhunsi, SJ | Done | Shuaib Reeyaz
Phase 3: ezMarker (app.py/app.php, grade_functions file?) | Deadline: Nov. 24
Segment | Python Status | Python Owner | Testing Status | Testing Owner | PHP Status | PHP Owner | Testing Status | Testing Owner
login, auth_token_handler, show_courses, logout | In-Progress | Chongju Mai |  |  | In-Progress | Sarah Johnston
modify_grade_max | In-Progress | Xiang Ke |  |  | In-Progress | Sarah Johnston |  | Shuaib Reeyaz
set_grades, show_upload | In-Progress | Luc Boulanger |  |  | In-Progress | Sarah Johnston |  | Shuaib Reeyaz
parse_file | In-Progress | Jacob Heard |  |  | In-Progress | Sarah Johnston
error_checking |  |  |  | Pirajeev Praba | In-Progress | Sarah Johnston