## SPMP
Created At | Completed At | Last Modified | Name | Assignee | Tags | Notes | Projects | Task Type | Resolution
2017-11-22 | 2017-11-23 | 2017-12-15 | Heroku is only for testing python, Apache will be used for release | Sophie | High Priority | Please change the appropriate sections of SPMP to reflect this | SPMP | Feedback | Completed
2017-11-21 | 2017-11-23 | 2017-12-15 | Document Deliverables | Sophie | High Priority | Missing analysis, design? Also need to pluralize or otherwise make clear 2 versions of everything (for php, python) What is "Client Feedback"? Also, from Project deliverables (on CP317 site): "User documentation... Documentation standards". So need to add "Documentation standards". Probably should also add "coding standards". Not sure what "user documentation" is... perhaps Help doc.? So that can also be added | SPMP | Feedback | Completed
2017-11-21 |  | 2017-11-23 | Should deadline (i.e. Constraint) be Dec. 15 but leave Dec. 6 as target? | Sophie | Low Priority |  | SPMP | Feedback
2017-11-20 | 2017-11-22 | 2017-11-22 | provide descriptions/links for technical resources section | Deep Raithatha | Medium Priority |  | SPMP | Feedback | Completed
2017-11-12 | 2017-11-20 | 2017-11-20 | 6.2 should include Heroku, AWS? | Troy Nechanicky | Medium Priority | Remove Dropbox? Change Google Docs to G Suite OR Google Docs AND Google Sheets. Change MS Word to Microsoft Office?(since using Excel for csv manipulation). *DO THESE miscellaneous tools even need to be mentioned? Else just have to keep adding. I think 5 different applications were used to make diagrams* | SPMP | Feedback | Completed
2017-11-12 | 2017-11-13 | 2017-11-13 | Don't need to say "(Python and PHP)." for 6.1 Design. | Sophie | Low Priority | Stands out that it is not elsewhere in 6.1 | SPMP | Feedback | Completed
2017-11-12 | 2017-11-12 | 2017-11-12 | 5.4 comment | Sophie | High Priority | A log of all tickets from September 2017 to December 2017. A document containing detailed descriptions of QA reports. suggest to combine into 1 line *ACTUALLY, why does 5.4 exist? Duplication of deliverables in section 1* | SPMP | Feedback | Completed
2017-11-12 | 2017-11-12 | 2017-11-12 | Conflicting due dates | Sophie | High Priority | Constraint says deadline of Dec. 6. 5.1.1 says deadline of Dec. 20. Deadline in 6.1 for intergration is 05 | SPMP | Feedback | Completed
2017-11-12 | 2017-11-13 | 2017-11-13 | Desire2Learn has been D2L for some years now. Remove Desire2Learn | Sophie | Medium Priority | Actually recommend copying Def'ns from Requirements. Don't like SPMP def for Brightspace either | SPMP | Feedback | Completed
2017-11-12 | 2017-11-12 | 2017-11-12 | Should add link to PHP website and then distinguish between the 2 | Sophie | High Priority | That is to correct existing Reference section. However, I recommend removing "test website". What is purpose of it on SPMP? Site does not actually reflect where ezMarker is tested (localhost) | SPMP | Feedback | Completed
2017-11-12 | 2017-11-12 | 2017-11-12 | Why are some documents excluded from deliverables | Sophie | High Priority | Deliverables missing documents listed in Documentation Responsibilities spreadsheet. If this is because they aren't required, I can see that point of view. However, "The following documents will be presented to the client:" should include things like QA report, ezEmployee report, etc., no? QA Report also missing from Schedule Summary (seems weird that above docs aren't in deliverables but are in schedule?) | SPMP | Feedback | Completed
2017-11-12 | 2017-11-13 | 2017-11-13 | Introduction Suggestions | Sophie | Medium Priority | '-Why is the problem with existing implementation (have to manually set feedback) mentioned in scope and not 1.0 -Don't need to mention Harold in 1.0 and 1.2 -Image of existing MLS interface makes more sense in 1.0 than 1.2 -*WHY DOES 1.2 exist at all? Only things unique to 1.2: problem with existing implementation (should be in 1.0 regardless) and 2 sentences describing what ezMarker does (file upload and manual entry). Recommend folding the 3 things just mentioned in 1.0 | SPMP | Feedback | Completed
2017-11-12 | 2017-11-13 | 2017-11-13 | Problems with ToC and Headings | Sophie | High Priority | Should be obvious | SPMP | Feedback | Completed
2017-11-12 | 2017-11-12 | 2017-11-12 | 5.2 Grammar / Voice based changes | Sophie |  | "If issue regards code: add an entry to QA document indication what actions caused said issue, and the involved parties." "indication" should be "indicating" based off present voice | SPMP
2017-11-12 | 2017-11-12 | 2017-11-12 | 1.5. Schedule Summary: Link to later section does not work | Sophie |  | "Refer toÂ Section 6.1Â of the SPMP for a detailed schedule of the project timeline." Underlined line is linked, but does nto go anywhere. | SPMP
2017-11-12 | 2017-11-12 | 2017-11-12 | 4.3 Grammer/Voice Based Changes | Sophie |  | "back-end Members" Should be "Back-end Members" to keep consistent with other titles "Keep QA log on tested software Should be "Keep logs on tested software" since bullet point already under the QA role, might be redundant putting QA again. | SPMP
2017-11-12 | 2017-11-12 | 2017-11-12 | 1.0 Overview: Grammar/Voice based changes | Sophie |  | "The current feedback system on MLS becomes tedious and is time consuming when giving feedback for large classes. ezMarker cuts down time by allowing bulk grade and feedback upload with the use of theÂ Brightspace API." "upload" should be "uploading" based off active voice definition. "becomes" should be "is' based off present active voice definition. "Although designed to reduce time spend grading programming assignments, uploading feedback from the Autograder still takes considerable amounts of time using the conventional MLS feedback system." "spend" should be "spent" grammar | SPMP
2017-10-17 | 2017-10-17 | 2017-10-21 | section 3: definition for SPMP is in a different format than rest, period needed at end as well | Lucas Boulanger | Low Priority |  | SPMP | Task | Completed
2017-10-17 | 2017-10-17 | 2017-10-21 | Add periods to the end of list items | Lucas Boulanger | Low Priority | periods at end of list items (up for discussion, but many lists are structured as sentences and should have periods) specifically sections: 1.3, 1.4, 4.3, 5.1.3, 5.2.1, 5.2.4, 5.4, 6.1, 7.1, 7.4 and any other I guess | SPMP | Feedback | Completed
2017-10-11 | 2017-10-21 | 2017-10-21 | Merge changes made in feat/test-feature branch | Lucas Boulanger | Medium Priority |  | SPMP | Feedback | Completed
2017-10-05 | 2017-10-12 | 2017-10-12 | All external links should open in a new tab | Sumeet Jhand | Low Priority |  | SPMP | Feedback
2017-10-05 | 2017-10-12 | 2017-10-12 | 1.4.1 Should be a list of the projects | Sophie | Medium Priority | "ezMarker Python version ezMarker PHP version Brightspace API Python Wrapper" | SPMP | Feedback | Completed
2017-10-05 | 2017-10-12 | 2017-10-12 | Flask should be a list item in 6.3 | Sumeet Jhand | Low Priority |  | SPMP | Feedback | Completed
2017-10-03 | 2017-10-21 | 2017-10-21 | Need to mention Autograder driving force behind project | Lucas Boulanger | Medium Priority | According to Brown | SPMP | Feedback | Completed
2017-10-02 | 2017-10-12 | 2017-10-12 | Links outside of the Definitions section should not be external | Sophie | Low Priority | Should instead link to Definitions section, which has external links. Otherwise what is the point of the Definition section | SPMP | Feedback | Completed
2017-10-01 | 2017-10-01 | 2017-10-05 | In 5.3 the last part of the sentence "Integration between frontend and backend may not work as expected and will be met with a meeting both teams" is missing a word and doesn't make sense. | Jaenuz Gorospe | Low Priority |  | SPMP | Feedback | Completed
2017-10-01 | 2017-10-01 | 2017-10-01 | Add brief summary of changes to Revision History | Troy Nechanicky | Low Priority | ex "updated based on feedback... added info about new wrapper and php project..." | SPMP | Feedback | Completed
2017-10-01 | 2017-10-12 | 2017-10-12 | No mention of 2 Wrappers or 2 Versions | Sophie | High Priority |  | SPMP | Feedback | Completed
2017-10-01 | 2017-10-01 | 2017-10-01 | 5.2 Table of Contents remove | Troy Nechanicky | Medium Priority | Section was deleted | SPMP | Feedback | Completed
2017-09-30 | 2017-10-01 | 2017-10-01 | Remove 7.1,7.6 or add content | Sophie | High Priority |  | SPMP | Feedback | Completed
2017-09-30 | 2017-10-01 | 2017-10-01 | Remove 5.2 or add content | Sarah Johnston | High Priority |  | SPMP | Feedback | Completed
2017-09-30 | 2017-10-01 | 2017-10-12 | Changes to 1.2 | Troy Nechanicky | Medium Priority | Suggest add "-Budget of $0" to Constraints, make only Assumption "Autograder outputting correct file" (current assumptions are just what software we will use, already covered in other sections and doesn't really fit the Assumptions purpose). | SPMP | Feedback | Completed
2017-09-27 | 2017-10-12 | 2017-10-12 | Need to mention building on existing project | Sophie | High Priority |  | SPMP | Feedback | Completed
2017-09-27 | 2017-09-30 | 2017-09-30 | Ensure project is referred to as ezMarker and not ezGrader | Troy Nechanicky | High Priority | mistake appears at least in section 1 | SPMP | Feedback | Completed
2017-09-27 | 2017-09-29 | 2017-10-12 | Update project timeline | Sophie | Low Priority |  | SPMP | Feedback
2017-09-27 | 2017-09-30 | 2017-09-30 | Reword last 2 sentences of 5.4 | Marko Mihailovic | Low Priority | Sentences are not good grammar | SPMP | Feedback | Completed
2017-09-27 | 2017-09-29 | 2017-09-29 | Number headings in 1.3, 1.4 | Jose Romero | Medium Priority | Confusing how 1.3, 1.4 subsections sections are just bolded headings and not numbered, even when there are a lot of them | SPMP | Feedback | Completed
2017-09-27 | 2017-09-29 | 2017-09-29 | Mention in 6.2 Flask, Apache, any other tech that will be used | Sophie | High Priority |  | SPMP | Feedback | Completed
2017-09-27 | 2017-09-30 | 2017-09-30 | Remove authors from top of doc. | Troy Nechanicky | Medium Priority | Authors covered in Revision History section. Also, make sure author section in Revision History is correct | SPMP | Feedback | Completed
2017-09-27 | 2017-09-30 | 2017-09-30 | Make reference hyperlinks to definition where applicable | Troy Nechanicky | Medium Priority | Add links where D2L, Brightspace API, etc. are mentioned in doc to Definition section in doc | SPMP | Feedback | Completed
2017-09-27 | 2017-09-29 | 2017-09-29 | 2017-03-01
2017-09-27 | 2017-09-29 | 2017-09-29 | 2017-05-04
2017-09-27 | 2017-09-29 | 2017-09-29 | 2017-07-06
2017-09-27 | 2017-10-01 | 2017-10-01 | 1.2 Add more detail | Troy Nechanicky | High Priority | Section too short, add in depth process of inputting grades (i.e. display the problem we are trying to solve) Will include making the target audience clear in 1.2 & 1.0. Also see Slack convo that is relevant: "Troy Nechanicky [6:40 PM]Â Req. introduction says "conventional feedback uploading techniques such as... through a Dropbox interface". Accurate? Could be better worded to expose problem with interface? (I'm already going to add that you have to manually enter grades for sometimes 200 students) Harold [7:01 PM]Â Wording could use some help. If you check my report from last winter I go into the manual methods a bit" | SPMP | Feedback | Completed
2017-09-27 | 2017-09-30 | 2017-10-21 | Use present tense and active voice | Troy Nechanicky | High Priority |  | SPMP | Feedback | Completed
2017-09-27 | 2017-09-29 | 2017-09-29 | 2017-03-01 | Jose Romero
2017-09-27 | 2017-09-29 | 2017-09-29 | 2017-05-04 | Marko Mihailovic
2017-09-27 | 2017-09-29 | 2017-09-29 | 2017-07-06 | Sophie
2017-09-27 | 2017-09-29 | 2017-09-29 | 1.1 Remove "etc." | Jose Romero | Medium Priority |  | SPMP | Feedback | Completed